## Summary
| Priority | Initial Estimate | Actual Time Spent | Work Hours Left | Progress
Project 1 | High | 97 | 24 | 14 | 10.31%
Project 2 | Medium | 7 | 7 | 7 | 0%
Extra Mile | Low | 12 | 12 | 12 | 0%
Total |  | 104 | 31 | 21 | 32.26%
Total (+ Extra) |  | 116 | 43 | 33 | 23.26%
Timeframe
Start Date | Deadline | Work Days Left | Weekend Days Left | Total Days Left
2022-06-20 | 2022-07-22 | 17.8571 | 6.8886 | 24.7457
Statistics
Estimated Velocity | Actual Velocity | Velocity needed for deadline | Current Velocity
3.5 h/day | 1.3 h/day | 1.3 h/day | 1.1 h/day
Formulas:
Initial Estimate = MAX(0,([Priority]-TODAY()+1)/7*5)

## Project 1
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 – Part 8
Task 1 | 1 | 1 | 0 | Done
Task 2 | 1 | 1 | 0 | Done
Task 3 | 1 | 1 |  | Done
Task 4 | 1 | 1 |  | Done
Task 5 | 1 | 1 |  | Done
Task 6 | 1 | 1 |  | Done
Task 7 | 1 | 1 |  | Done
Task 8 | 1 | 1 |  | Done
Task 9 | 1 | 1 |  | Done
Task 10 | 1 | 1 |  | Done
Task 11 | 1 |  |  | Not Started
Task 12 | 1 |  |  | Not Started
Task 13 | 1 |  |  | Not Started
Task 14 | 1 |  |  | Not Started
Task 15 | 1 |  |  | Not Started
Milestone 2 – Part 9
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 | 1 | 1 | Not Started
Task 4 | 1 | 1 | 1 | Not Started
Task 5 | 1 |  |  | Not Started
Task 6 | 1 |  |  | Not Started
Task 7 | 1 |  |  | Not Started
Task 8 | 1 |  |  | Not Started
Task 9 | 1 |  |  | Not Started
Task 10 | 1 |  |  | Not Started
Task 11 | 1 |  |  | Not Started
Task 12 | 1 |  |  | Not Started
Milestone 3 – Part 10
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 |  |  | Not Started
Task 4 | 1 |  |  | Not Started
Task 5 | 1 |  |  | Not Started
Task 6 | 1 |  |  | Not Started
Task 7 | 1 |  |  | Not Started
Task 8 | 1 |  |  | Not Started
Task 9 | 1 |  |  | Not Started
Task 10 | 1 |  |  | Not Started
Task 11 | 1 |  |  | Not Started
Task 12 | 1 |  |  | Not Started
Task 13 | 1 |  |  | Not Started
Task 14 | 1 |  |  | Not Started
Task 15 | 1 |  |  | Not Started
Task 15 | 1 |  |  | Not Started
Task 15 | 1 |  |  | Not Started
Milestone 4 – Part 11
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 |  |  | Not Started
Task 4 | 1 |  |  | Not Started
Task 5 | 1 |  |  | Not Started
Task 6 | 1 |  |  | Not Started
Task 7 | 1 |  |  | Not Started
Task 8 | 1 |  |  | Not Started
Task 9 | 1 |  |  | Not Started
Task 10 | 1 |  |  | Not Started
Task 11 | 1 |  |  | Not Started
Task 12 | 1 |  |  | Not Started
Task 13 | 1 |  |  | Not Started
Milestone 5 – Part 12
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 |  |  | Not Started
Task 4 | 1 |  |  | Not Started
Task 5 | 1 |  |  | Not Started
Task 6 | 1 |  |  | Not Started
Task 7 | 1 |  |  | Not Started
Task 8 | 1 |  |  | Not Started
Task 9 | 1 |  |  | Not Started
Task 10 | 1 |  |  | Not Started
Task 11 | 1 |  |  | Not Started
Task 12 | 1 |  |  | Not Started
Milestone 6 – Part 13
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 |  |  | Not Started
Task 4 | 1 |  |  | Not Started
Task 5 | 1 |  |  | Not Started
Task 6 | 1 |  |  | Not Started
Task 7 | 1 |  |  | Not Started
Task 8 | 1 |  |  | Not Started
Task 9 | 1 |  |  | Not Started
Task 10 | 1 |  |  | Not Started
Task 11 | 1 |  |  | Not Started
Task 12 | 1 |  |  | Not Started
Task 13 | 1 |  |  | Not Started
Milestone 7 – Part 14
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 |  |  | Not Started
Task 4 | 1 |  |  | Not Started
Task 5 | 1 |  |  | Not Started
Task 6 | 1 |  |  | Not Started
Task 7 | 1 |  |  | Not Started
Task 8 | 1 |  |  | Not Started
Task 9 | 1 |  |  | Not Started
Task 10 | 1 |  |  | Not Started
Task 11 | 1 |  |  | Not Started
Task 12 | 1 |  |  | Not Started
Task 13 | 1 |  |  | Not Started
Task 14 | 1 |  |  | Not Started
Task 15 | 1 |  |  | Not Started

## Project 2
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 1 | 1 | 1 | Not Started
Task 2 | 1 | 1 | 1 | Not Started
Task 3 | 1 | 1 | 1 | Not Started
Task 4 | 1 | 1 | 1 | Not Started
Task 5 | 1 | 1 | 1 | Not Started
Task 6 | 1 | 1 | 1 | Not Started
Task 7 | 1 | 1 | 1 | Not Started

## Extra Mile
Task Description | Initial Estimate | Final Estimate | Days Left | Status
Milestone 1 - TODO
Task 1 | 2 | 2 | 2 | Not Started
Task 2 | 2 | 2 | 2 | Not Started
Task 3 | 2 | 2 | 2 | Not Started
Task 4 | 2 | 2 | 2 | Not Started
Task 5 | 2 | 2 | 2 | Not Started
Task 6 | 2 | 2 | 2 | Not Started

## Gotchas
When you duplicate a tab, all named ranges will automatically be duplicated as well with name SHEET!ORIGINAL_NAME. In most cases, this is fine and there is nothing explicit you should change in that sheet. What you have to update, though, is the project row in the "Summary" sheet. Use some of the others as reference what to put there.
Renaming a sheet will not break your statistics in the "Summary " sheet.
There is a hidden column D in all your project tabs. It contains some numbers which are used to calcuate remaining and current velocity. Make sure the formulas in those columns are not broken, otherwise your stats will be incorrect.